## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | J Rakshitha | 2026-07-04 | 'pip install -r requirements.txt' failed while trying to compile pydantic-core from source (Rust/MSVC linker error) on Windows with Python 3.13. | Sprint 1 | J Rakshitha | Others | requirements.txt pinned an old exact pydantic version with no prebuilt wheel for Python 3.13. Removed strict '==' pins in favor of flexible '>=' minimum versions, letting pip resolve to an already-compatible newer build. | 2026-07-04 | Closed | Verified clean install completes without any compilation step.
2 | J Rakshitha | 2026-07-04 | StatCard component's accent color classes were built via Tailwind class-name string interpolation (e.g. bg-accent-${accent}), which Tailwind's static class scanner cannot detect, so the intended colors would have silently never rendered. | Sprint 1 | J Rakshitha | User Interface | Replaced the interpolated class names with a literal, fully-spelled-out class map so Tailwind's scanner can detect every class at build time. | 2026-07-04 | Closed | Self-caught during code review, before it ever reached the live demo.
3 | J Rakshitha | 2026-07-04 | POST /api/incidents/ingest-metrics returned HTTP 500 Internal Server Error when creating a new incident record. | Sprint 1 | J Rakshitha | Logical | Found a missing SQLAlchemy back_populates relationship: RemediationAction had no 'incident' attribute matching Incident.actions. Added the missing relationship() to fix the ORM mapper configuration. | 2026-07-04 | Closed | Confirmed fixed after backend restart; incident creation now returns HTTP 200.
4 | J Rakshitha | 2026-07-04 | Frontend dashboard displayed 'Backend not reachable' on every page even though the FastAPI server was confirmed running. | Sprint 1 | J Rakshitha | Others | Root cause was a CORS origin mismatch: Vite had auto-selected port 5174 (5173 was already in use) but the backend only allowed 5173. Updated CORSMiddleware to accept any localhost/127.0.0.1 port via allow_origin_regex. | 2026-07-04 | Closed | Verified live data loading correctly on Overview, Dev-Collaboration and Incident Response tabs.
5 | J Rakshitha | 2026-07-05 | Dark/Light theme toggle button changed internal state on click but produced no visible change in the UI colors. | Sprint 1 | J Rakshitha | User Interface | Light-theme color values were never defined; only a dark palette existed. Implemented CSS custom properties for both themes (:root for dark, html.light overrides) and mapped every Tailwind color token to them. | 2026-07-05 | Closed | Confirmed both themes render correctly across all pages after fix.
6 | J Rakshitha | 2026-07-18 | The Tool Selector's rule-based fallback can tie-break toward 'create_escalation_ticket' instead of a more specific tool (e.g. restart_service) when the situation text happens to contain a severity keyword like 'P1' alongside a remediation keyword, because the first-registered tool wins ties. | Sprint 2 | J Rakshitha | Logical | Not yet fixed — logged for future refinement of the tie-breaking rule (e.g. weight keyword specificity instead of first-match-wins). | 2026-07-18 | Open | Non-blocking: the selected tool is still a valid, explainable choice; no incorrect or crashing behavior. Low priority.
8 | J Rakshitha | 2026-07-28 | GitHub webhook POST returned HTTP 401 Invalid signature — ngrok reachable but HMAC verification failed. | Sprint 3 | J Rakshitha | Logical | Aligned GitHub repo webhook secret with GITHUB_WEBHOOK_SECRET in backend/.env via API PATCH; added signature to pytest. | 2026-07-28 | Closed | Recent Deliveries shows 200 OK; manual and webhook sync both work.
10 | J Rakshitha | 2026-07-30 | google-genai SDK returned 429 quota exceeded for gemini-2.0-flash with AQ auth key. | Sprint 3 | J Rakshitha | Others | Switched default LLM_MODEL to gemini-flash-latest in config.py and .env; verified used_llm=True in live test. | 2026-07-30 | Closed | LLM badge appears on Code Review and Tool Selector agents in demo.
7 | J Rakshitha | 2026-08-01 | GET /api/incidents/ returned HTTP 500 on existing SQLite database — OperationalError: no such column incidents.sla_minutes. | Sprint 3 | J Rakshitha | Logical | Created Alembic migration 001_add_incident_sla_fields and documented 'alembic upgrade head' in README. | 2026-08-01 | Closed | Incidents API returns 200; SLA fields visible on AIOps cards.
9 | J Rakshitha | 2026-08-03 | Dev-Collab 'Simulate Conflict' displayed misleading 'Backend not reachable' error after ~10 seconds. | Sprint 3 | J Rakshitha | User Interface | Increased simulateDemoConflict and simulateIncident axios timeout from 10s to 45s; improved error message for ECONNABORTED. | 2026-08-03 | Closed | Simulate Conflict completes in ~15s and shows conflict + notifications.
11 | J Rakshitha | 2026-08-04 | Discord webhook test returned 401 when webhook URL was revoked and regenerated in channel settings. | Sprint 3 | J Rakshitha | Others | Updated DISCORD_WEBHOOK_URL in .env and re-ran POST /api/system/test-discord-webhook. | 2026-08-04 | Closed | Discord #ai-alerts receives Dev-Collab and AIOps alerts.
12 | J Rakshitha | 2026-08-04 | GET /api/dev-collab/conflicts returned HTTP 500 — OperationalError: no such column conflict_events.discovery_context after enterprise model update. | Sprint 3 | J Rakshitha | Logical | Applied Alembic migration 002_enterprise_intelligence; added root pytest.ini for async tests from project root. | 2026-08-04 | Closed | Conflicts API returns discovery_context, semantic_analysis, quality_report; 55 tests pass.
13 | J Rakshitha | 2026-08-06 | React frontend rendered a blank white screen — all pages empty although Vite dev server was running. | Sprint 4 | J Rakshitha | User Interface | Added missing export default statement to frontend/src/services/apiClient.js so AppConfigContext and pages could import the client. | 2026-08-06 | Closed | Dashboard, Dev-Collab, Workflows, and Monitoring pages load correctly.
14 | J Rakshitha | 2026-08-07 | POST /api/workflows/runs/{id}/resume returned HTTP 400 Invalid status when workflow run was queued by background job queue. | Sprint 4 | J Rakshitha | Logical | Extended resume_workflow_internal to accept queued status in addition to waiting_hitl before executing HITL resume. | 2026-08-07 | Closed | HITL resume completes; live_smoke_test workflow step passes.
15 | J Rakshitha | 2026-08-08 | live_smoke_test.py failed at workflow HITL gate — start returned status queued and test expected waiting_hitl immediately. | Sprint 4 | J Rakshitha | Logical | Added polling loop in live_smoke_test.py to wait until workflow status is waiting_hitl or completed. | 2026-08-08 | Closed | live_smoke_test reports 9/9 PASS including HITL workflow.
16 | J Rakshitha | 2026-08-09 | Backend startup blocked ~30 seconds when REDIS_URL=redis://localhost:6379/0 was set without a local Redis server. | Sprint 4 | J Rakshitha | Others | Added connect timeout and in-memory job queue fallback when Redis is unreachable; documented commenting REDIS_URL for local dev. | 2026-08-09 | Closed | Backend starts in under 3s; job queue works with memory fallback.
17 | J Rakshitha | 2026-08-05 | GET /api/workflows/definitions returned HTTP 500 — OperationalError: no such table workflow_runs after adding orchestration models. | Sprint 4 | J Rakshitha | Logical | Applied Alembic migration 004_workflow_orchestration to create workflow_runs and workflow_step_logs tables. | 2026-08-05 | Closed | Workflow definitions and start API return HTTP 200.
18 | J Rakshitha | 2026-08-10 | POST /api/incidents/ingest-metrics updated the same incident instead of creating a new card per click. | Sprint 4 | J Rakshitha | Logical | Removed ingest upsert; each request inserts a new incident with source=ingest and JWT triggered_by. | 2026-08-10 | Closed | Each Send Real Test Metrics click adds a new INGEST card.
19 | J Rakshitha | 2026-08-11 | Simulate Incident cards still appeared in the live AIOps feed and mixed with real ingest history. | Sprint 4 | J Rakshitha | User Interface | visible_feed_incidents hides simulate; keeps ingest/webhook/monitoring for 6 hours. | 2026-08-11 | Closed | Live feed shows only real sources with INGEST / WEBHOOK / MONITORING badges.
20 | J Rakshitha | 2026-08-12 | Coordinator linked a checkout-service incident to an unrelated GitHub PR that did not touch checkout. | Sprint 4 | J Rakshitha | Logical | Strict file-keyword match to service_name; removed weak any-open-PR fallback. | 2026-08-12 | Closed | Incidents link to GitHub only when the file matches the affected service.
21 | J Rakshitha | 2026-08-13 | Team Notifications listed seed demo names Priya Sharma, Arjun Mehta, Sneha Reddy, and Karthik Rao. | Sprint 4 | J Rakshitha | User Interface | is_visible_notification_recipient hides seed names and generic team labels. | 2026-08-13 | Closed | Notifications show real GitHub/ops names only.
22 | J Rakshitha | 2026-08-14 | External Lookup mixed public Chaos Monkey and o11yParty GitHub issues into incident references. | Sprint 4 | J Rakshitha | Logical | sanitize_external_references keeps only the configured repository. | 2026-08-14 | Closed | Incident GitHub refs stay on the configured repo.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others